## Slide 1: Software Engineering
Lecture 11
Risk Analysis and Management

## Slide 2: Reactive Risk Management
Project team reacts to risks when they occur.
More commonly, the software team does nothing about risks until something goes wrong.
Then, the team involved into action in an attempt to correct the problem rapidly. This is often called a fire fighting mode.
When this fails, “crisis management” takes over and the project is in real jeopardy.

## Slide 3: Proactive Risk Management
A proactive strategy begins long before technical work is initiated.
Potential risks are identified, their probability and impact are assessed, and they are ranked by importance.
Then, the software team establishes a plan for managing risk.
The primary objective is to avoid risk, but because not all risks can be avoided, the team works to develop a contingency plan that will enable it to respond in a controlled and effective manner.

## Slide 4: Software Risks
Risk always involves two characteristics:
  Uncertainty —the risk may or may not happen; that is, there are no 100% probable risks.
  Loss—if the risk becomes a reality, unwanted consequences or losses will occur
When risks are analyzed, it is important to quantify the level of uncertainty and the degree of loss associated with each risk.
To accomplish this, different categories or types of risks are considered.
  Project Risks
  Technical Risks
  Business Risks
  Known Risks.
  Predictable Risks
  Unpredictable Risks

## Slide 5: Project Risk
Project risks make threats the project plan.
That is, if project risks become real, it is likely that project schedule will slip and that costs will increase.
Project risks identify potential budgetary, schedule, personnel (staffing and organization), resource, customer, and requirements problems and their impact on a software project.
Project complexity, size, and the degree of structural uncertainty were also defined as project risk factors.

## Slide 6: Technical risks
Technical risks threaten the quality and timeliness of the software to be produced.
If a technical risk becomes a reality, implementation may become difficult or impossible.
Technical risks identify potential design, implementation, interface, verification, and maintenance problems.
In addition, specification ambiguity, technical uncertainty, and "leading-edge" technology are also risk factors.

## Slide 7: Business Risk
Business risks threaten the feasibility of the software to be built.
Business risks often jeopardize the project or the product.
Top five business risks are
  Building a excellent product or system that no one really wants (market risk),
  Building a product that no longer fits into the overall business strategy for the company (strategic risk)
  Building a product that the sales force doesn't understand how to sell.
  Losing the support of senior management due to a change in focus or a change in people (management risk)
  Losing budgetary or personnel commitment (budget risks)

## Slide 8: Known Risk
Known risks are those that can be uncovered after careful evaluation of the project plan, the business and technical environment in which the project is being developed,
Other reliable information sources (e.g., unrealistic delivery date, lack of documented requirements or software scope, poor development environment).

## Slide 9
Predictable risks are generalized from past project experience (e.g., staff turnover, poor communication with the customer, etc).
Unpredictable risks are the joker in the deck. They can and do occur, but they are extremely difficult to identify in advance.

## Slide 10: Risk Identification
Risk identification is a systematic attempt to specify threats to the project plan (estimates, schedule, resource loading, etc.).
By identifying known and predictable risks, the project manager takes a first step toward avoiding them when possible and controlling them when necessary.
Two distinct types of risks
  Generic risks are a potential threat to every software project
  Product-specific risks can be identified only by those with a clear understanding of the technology, the people, and the environment that is specific to the project at hand.

## Slide 11: Contd.
To identify product-specific risks, the project Plan and the software statement of scope are examined.
One method for identifying risks is to create a risk item checklist.
The checklist can be used for risk identification and focuses on some subset of known and predictable risks in the following generic subcategories:
Product size —risks associated with the overall size of the software to be built or modified.
Business impact —risks associated with constraints imposed by management or the marketplace.

## Slide 12: Risk Item Checklist contd.
Customer characteristics —risks associated with the sophistication of the customer and the developer's ability to communicate with the customer in a timely manner.
Process definition —risks associated with the degree to which the software process has been defined and is followed by the development organization.
Development environment —risks associated with the availability and quality of the tools to be used to build the product.
Technology to be built —risks associated with the complexity of the system to be built and the "newness" of the technology that is packaged by the system.
Staff size and experience —risks associated with the overall technical and project experience of the software engineers who will do the work.

## Slide 13: Risk Components
PM identify the risk drivers that affect software risk components:
Performance risk—the degree of uncertainty that the product will meet its requirements and be fit for its intended use.
Cost risk—the degree of uncertainty that the project budget will be maintained.
Support risk—the degree of uncertainty that the resultant software will be easy to correct, adapt, and enhance.
Schedule risk—the degree of uncertainty that the project schedule will be maintained and that the product will be delivered on time.

## Slide 14: The impact of each risk driver on the risk component

## Slide 15: Risk Projection
Risk projection, also called risk estimation, attempts to rate each risk in two ways:
  The likelihood or probability that the risk is real.
  the consequences (i.e. effect or result) of the problems associated with the risk, should it occur.
The project planner, along with other managers and technical staff, performs four risk projection activities:
  Establish a scale that reflects the supposed likelihood of a risk
  Describe the consequences of the risk,
  Estimate the impact of the risk on the project and the product,
  Note the overall accuracy of the risk projection so that there will be no misunderstanding
The intent of these steps is to consider risks in a manner that leads to prioritization. By prioritizing risks, the team can allocate resources where they will have the most impact.

## Slide 16: Developing Risk Table

## Slide 17: Procedure to build risk table
Listing all risks in first column. This can be accomplished with the help of the risk item checklists
Each risk is categorized in the second column
The probability of occurrence of each risk is entered in the next column of the table. Which can be estimated by team members.
Impact of each risk is assessed. Each risk component is assessed using the characterization and an impact categories like catastrophic, critical, marginal and negligible are determined.
Once table is completed, manger will give order of prioritization to the risk. Therefore, the table is sorted by probability and by impact.

## Slide 18: Contd.
High-probability, high-impact risks get into the top of the table, and low-probability risks drop to the bottom. (First order prioritization).
The project manager studies the resultant sorted table and defines a cutoff line.
The cutoff line implies that only risks that lie above the line will be given further attention.
Risks that fall below the line are considered as second-order prioritization.

## Slide 19: Contd.
Risk impact and probability have a distinct influence on management concern.
Risk factor that has a high impact but a very low probability of occurrence then management will give little attention or some time no attention.
But if risk factor that has high impact and high probability of occurrence then management will give high attention.
All risks that lie above the cutoff line must be managed and specify in last column of the table under RMMM column.

## Slide 20: Contd.

## Slide 21: Assessing Risk Impact
Three factors affect the consequences that are likely if a risk does occur:
  Nature,
  Scope, and
  Timing.
The nature of the risk indicates the problems that are likely if it occurs.
For example, a technical risk, development environment change
The scope of a risk combines the strictness with its overall distribution.
For ex. how much of the project will be affected
or how many customers are harmed?
The timing of a risk considers when and for how long the impact will be felt.

## Slide 22: To determine the overall consequences of a risk:
Determine the average probability of occurrence value for each risk component.
Determine the impact for each component based on the criteria.
Complete the risk table and analyze the results as described
Now measure, Risk exposure (RE).
RE = P x C
P is the probability of occurrence for a risk and C is the cost to the project.

## Slide 23: Example- the software team defines a project risk in the following manner
Risk Identification - Only 70 percent of the software components scheduled for reuse and remaining functionality will have to be custom developed.
Risk probability. 80% (likely).
Risk Impact – Assume total no. of component is 60. If only 70 percent can be used, 18 components would have to be developed from scratch.
Since the average component is 100 LOC and local data indicate that the software engineering cost for each LOC is $14.00,
the overall cost (impact) to develop the components would be
18 x 100 x 14 = $25,200.
Risk exposure. RE = 0.80 x 25,200 ~ $20,200.

## Slide 24: Contd.
once an estimate of the cost of the risk is derived, compute RE for each risk in risk table.
The total risk exposure for all risks (above the cutoff in the risk table) can provide a means for adjusting the final cost estimate for a project.
The project team should revisit the risk table at regular intervals, re-evaluating each risk to determine when new circumstances cause its probability and impact to change.
As a consequence of this activity, it may be necessary to add new risks to the table, remove some risks that are no longer relevant, and change the relative positions of still others.
Compare RE for all risks to the cost estimate for the project. If RE is greater than 50 percent of project cost, the feasibility of the project must be evaluated.

## Slide 25: Risk Mitigation, Monitoring, and Management
Risk analysis goal - to assist the project team in developing a strategy for dealing with risk. An effective strategy must consider three issues:
    Risk avoidance or mitigation.
    Risk monitoring
    Risk management and contingency planning
Proactive approach to risk, avoidance is always the best strategy. This is achieved by developing a plan for risk mitigation.
For example, assume that high staff turnover (i.e. revenue) is noted as a project risk.

## Slide 26
To mitigate this risk, project management must develop a strategy for reducing turnover.
Steps are:
  Meet with current staff to determine causes for turnover (e.g., low pay, competitive job market).
  Mitigate those causes that are under our control before the project starts.
  Organize project teams so that information about each development activity is widely dispersed.
  Define documentation standards and establish mechanisms to be sure that documents are developed in a timely manner.
  Conduct peer reviews of all work
  Assign a backup staff member for every critical technologist.

## Slide 27
As the project proceeds, risk monitoring activities commence.
The project manager monitors factors that may provide an indication of whether the risk is becoming more or less likely.
In the case of high staff turnover, the following factors can be monitored:
  General attitude of team members based on project pressures.
  Potential problems with compensation and benefits.
  The availability of jobs within the company and outside it.
Risk management and contingency planning assumes that mitigation efforts have failed and that the risk has become a reality.

## Slide 28
The project is well underway and a number of people announce that they will be leaving. If the mitigation strategy has been followed, backup is available, information is documented, and knowledge has been dispersed across the team.
In addition, the project manager may temporarily refocus resources (and readjust the project schedule) to those functions that are fully staffed, enabling newcomers who must be added to the team to “get up to speed.”
Those individuals who are leaving are asked to stop all work and spend their last weeks in “knowledge transfer mode.”
This might include video-based knowledge capture, the development of “commentary documents,” and/or meeting with other team members who will remain on the project.
RMMM steps incur additional project cost. For example, spending the time to "backup" every critical technologist costs money.

## Slide 29: THE RMMM PLAN
The RMMM plan documents all work performed as part of risk analysis and is used by the project manager as part of the overall project plan.
Some software teams do not develop a formal RMMM document. Rather, each risk is documented individually using a risk information sheet (RIS).
RIS is maintained using a database system, so that creation and information entry, priority ordering, searches, and other analysis may be accomplished easily.
Once RMMM has been documented and the project has begun, risk mitigation and monitoring steps commence.